## Operational Risk Register
Risk ID | Risk Title | Risk Domain | Business Impact Category | Risk Description | Inherent Risk Assessment |  |  | Residual Risk Assessment |  |  | Risk Category | Priority | Mitigating Actions | Current PoA | Departmental Objective | Executive Goal | Risk Decision | Risk Owner | Current Action |  | Risk Status | Last Reviewed
[5 empty] | Likelihood | Impact | Score | Likelihood | Impact | Score | [8 empty] | Task | Target Date
R - 003 | Configuration Backup Missing | Operations | Operational | If network device configurations are lost and no backups exist, infrastructure becomes vulnerable to prolonged recovery time resulting in operational downtime. | 4 | 4 | 16 | 4 | 2 | 8 |  | 1 | Network Configuration Backup Policy v1.1 | Configuration Recovery Procedure v1.1 | Configuration Recovery Procedure v1.1 | Configuration Recovery Procedure v1.1 | Mitigate | IT Infrastructure Manager | Annual review | 2027-02-01 | Accepted | 2026-04-01
R - 008 | Lack of Network Monitoring | Operations | Operational | If network monitoring is absent, failures may remain undetected resulting in prolonged operational disruption. | 4 | 4 | 16 | 4 | 4 | 16 |  | 2 | Network Operational Verification Policy v1.0 | Network Operational Verification Procedure v1.0 | Implement basic network monitoring capability | Centralized network monitoring and alerting platform | Mitigate | IT Infrastructure Manager | Design and Implement an In-House Network Monitoring Capability | 2026-04-08 | In Progress | 2026-04-08
R - 010 | Lack of Change Management | Operations | Operational | If network changes are implemented without formal change control, the infrastructure becomes vulnerable to configuration errors resulting in service outages. | 4 | 4 | 16 | 4 | 4 | 16 |  | 3 | [8 empty] | Open | 2026-03-08
R - 001 | Core Router Failure | Infrastructure | Operational | If the single inter-VLAN router fails while acting as the network gateway, the network becomes vulnerable to total internal connectivity loss resulting in operational disruption. | 3 | 5 | 15 | 3 | 5 | 15 |  | 4 | [8 empty] | Open | 2026-03-08
R - 009 | Uncontrolled Administrative Access | Security | Operational | If administrative access is not properly controlled, network devices become vulnerable to unauthorized configuration changes resulting in operational disruption. | 3 | 5 | 15 | 3 | 5 | 15 |  | 5 | [8 empty] | Open | 2026-03-08
R - 002 | Access Switch Failure | Infrastructure | Operational | If an access switch fails without redundancy, connected departments become vulnerable to complete network isolation resulting in service disruption. | 3 | 4 | 12 | 3 | 4 | 12 |  | 6 | [8 empty] | Open | 2026-03-08
R - 006 | DHCP Service Failure | Infrastructure | Operational | If the DHCP service fails, client devices become vulnerable to loss of IP assignment resulting in network access disruption. | 3 | 4 | 12 | 3 | 4 | 12 |  | 7 | [8 empty] | Open | 2026-03-08
R - 007 | DNS Service Failure | Infrastructure | Operational | If DNS services fail, users become vulnerable to inability to locate services resulting in widespread service disruption. | 3 | 4 | 12 | 3 | 4 | 12 |  | 8 | [8 empty] | Open | 2026-03-08
R - 011 | Network Capacity Exhaustion | Infrastructure | Strategic | If network capacity is exceeded during growth, the infrastructure becomes vulnerable to congestion resulting in degraded performance and service disruption. | 3 | 4 | 12 | 3 | 4 | 12 |  | 9 | [8 empty] | Open | 2026-03-08
R - 004 | VLAN Misconfiguration | Operations | Operational | If VLAN configuration errors occur during network expansion, the network becomes vulnerable to segmentation failure resulting in service disruption or traffic leakage. | 3 | 3 | 9 | 3 | 3 | 9 |  | 10 | [8 empty] | Open | 2026-03-08
R - 005 | IPv6 Misconfiguration | Infrastructure | Operational | If IPv6 addressing or routing is misconfigured, devices become vulnerable to connectivity failures resulting in partial network disruption. | 3 | 3 | 9 | 3 | 3 | 9 |  | 11 | [8 empty] | Open | 2026-03-08
R - 012 | Network Documentation Missing | Operations | Operational | If infrastructure documentation is missing or incomplete, recovery operations become vulnerable to delays resulting in prolonged outages. | 3 | 3 | 9 | 3 | 3 | 9 |  | TBD | [8 empty] | Open | 2026-03-08
R - 013
R - 014
R - 015
R - 016
R - 017
R - 018
R - 019
R - 020
R - 021
R - 022
R - 023
R - 024
R - 025
R - 026
R - 027
R - 028
R - 029
R - 030
R - 031
R - 032
R - 033
R - 034
R - 035
R - 036
R - 037
R - 038
R - 039
R - 040
R - 041
R - 042
R - 043
R - 044
R - 045
R - 046
R - 047
R - 048
R - 049
R - 050
R - 051
R - 052
R - 053
R - 054
R - 055
R - 056
R - 057
R - 058
R - 059
R - 060
R - 061
R - 062
R - 063
R - 064
R - 065
R - 066
R - 067
R - 068
R - 069
R - 070
R - 071
R - 072
R - 073
R - 074
R - 075
R - 076
R - 077
R - 078
R - 079
R - 080
R - 081
R - 082
R - 083
R - 084
R - 085
R - 086
R - 087
R - 088
R - 089
R - 090
R - 091
R - 092
R - 093
R - 094
R - 095
R - 096
R - 097
R - 098
R - 099
R - 100
Note on A1: Risk ID is a unique identifier for each risk to enable clarity and tracebility
Note on B1: Risk title is a easy to use name for commo usage
Note on E1: Category refers to the business impact if this risk is realised
Note on F1: Base Risk Assessment is the calulation of the inherit risk if this risk without mitigating actions
Note on I1: Base Risk Assessment is the calulation of the mitigated risk if this risk with mitigating actions
Note on L1: Risk Category is a level of danger this risk has to busines surival
Note on M1: Priority is the seqeunce which executive staff want to be address
Note on N1: Mitigating Actions are all the actions implemented to reduce the risk.
Note on O1: The Current Plan of Action is the plan to be executed if the risk is materialise at this moment.
Note on P1: The limited goal is the risk action plan to be achieved within local authority of risk
Note on Q1: The Executive Goal the risk action plan to be achieve with company's authority
Note on R1: The Executive Goal the risk action plan to be achieve with company's authority
Note on S1: The Risk Owner is the custodian of the risk and responsible to ensure risk mitigation and improvement is pursued
Note on T1: The Current Action plan is the what is administratively done with target dat of those actions to achieve risk mitigation goals.

## Data Control Sheet
Risk Domains | Business Impact Category | Likelihood Score | Impact Score | Risk Decision | Risk Status
Infrastructure | Operational | 1 | 1 | Mitigate | Open
Security | Financial | 2 | 2 | Accept | In Progress
Operations | Reputational | 3 | 3 | Transfer | Monitoring
Compliance | Legal / Compliance | 4 | 4 | Avoid | Accepted
Application | Strategic | 5 | 5 |  | Closed
Network
Data
Third Party